## Milestones
Milestones | Details
Concept Art | Unite team around a similar vision of what this game should look like for visuals, designs, gameplay, and mechanics
Main Menu | Basic game menu with New Game button, Settings button, and Quit button
Basic Game Manager | System to allow the game to start with a basic test level, player character, and enemy
Test Level w/ Player Character | Basic level with a basic player object, minimal level geography for testing
Player Movement | Player movement such as left/right, jump, roll/dash, climb, fly/float or double jump
Player Abilities | Player actions such as a basic attack and block
Test Enemy | Inert enemy which can be attacked, takes damage, has no behavior of its own
Test Items 1 & 2 | Basic items which affects base player stats, i.e movement speed, health, damage
Test Items 3 & 4 | Non-basic items which add, enhance, or alter player abilities, i.e extra jump, grapple hook, attack effects
Test Item Interactions | Items which affect the same thing should have a combined effect rather than a replacement effect
Enemy Movement | Basic enemy movement/pathing towards the player within a given range
Enemy Attacks | Enemy attack abilities, damage to player, knockback/stun, player invincibility frames
Player Animations | Get player movement to look fluid and move in a natural way
Enemy Animations | Get enemy movement to look fluid and move in a natural way
Level Designs | More detailed level designs with enemy spawns, item spawns, room encounters, etc
Test Boss | Big Bad enemy, must be defeated before moving to next level, dedicated room encounter
Full Boss | Flesh out Boss attacks/mechanics and animations
Art Assets | Create art assets for enemies, items, level environments
More Enemies | Enemies with unique attacks and mechanics
More Items | Items with unique effects and synergies
More Bosses | Unique boss enemies set for each stage
Music | Find, use, and get music to work well with the visuals
Save/Continue Game in Progress | Save gamestate locally and be able to return to a game in progress

## Timelines
Task Number | Tasks | Start Date | End Date | Lead Person
0 | Design and impelment the ability set of one unique character | 2024-10-06 | 2025-01-26 | Everyone
1 | Design a respawn area for players to re-enter the game after dying | 2024-11-24 | 2025-01-05 | Hari Koirala
2 | Implement composition for projectiles to enhance modularity and facilitate future expansions | 2024-11-03 | 2025-01-12 | Hari Koirala
3 | Develop projectile functionality to ensure they behave as intended within the game | 2024-12-08 | 2025-01-05 | Hari Koirala
4 | Research methods for creating a responsive player UI that adapts to different screen sizes and resolutions | 2024-10-07 | 2024-11-03 | Hari Koirala
5 | Create a system for playing and managing character animations to enhance visual feedback during gameplay | 2024-11-10 | 2024-12-08 | Hari Koirala
6 | Create a global signal system to handle events like onhit, ondamaged, enemydeath, for statistic tracking and passive activations | 2024-11-03 | 2025-01-05 | Bailin Zhen
7 | Implement a sfx system into base character and base enemy scenes | 2024-11-10 | 2024-12-08 | Bailin Zhen
8 | Design a standard way to hook up sounds to the sfx system in child character and enemy scenes | 2024-12-22 | 2025-02-09 | Bailin Zhen
9 | Find, Purchase, or somehow Acquire all sounds and music needed for the game in the form of .wav files | 2024-10-06 | 2024-11-10 | Bailin Zhen
10 | Develop a modular control scheme to be later modifiable by the UI Settings sytem | 2024-11-24 | 2024-12-15 | Bailin Zhen
11 | Develop music and sound effects for levels, game events, or player actions | 2024-10-20 | 2024-11-10 | Vitta Silberberg
12 | Design sprite sheets, art, and textures for game visuals and levels | 2024-10-13 | 2024-12-22 | Vitta Silberberg
13 | Research level design for creating levels that feel fun to play through and explore | 2024-10-06 | 2024-10-20 | Vitta Silberberg
14 | Design and implement player movement abilities and upgrades | 2024-12-01 | 2025-01-19 | Vitta Silberberg
15 | Design unique discoverable items and discoverable upgrades | 2024-11-17 | 2025-02-09 | Vitta Silberberg
16 | Design customizations for charater design | 2024-12-08 | 2025-01-26 | Matthew Estes
17 | Develop detection and jump ability | 2024-10-27 | 2024-11-17 | Matthew Estes
18 | Research optimization for projectile movement | 2024-11-17 | 2024-12-29 | Matthew Estes
19 | Document the progress as the project moves along | 2024-10-06 | 2025-04-06 | Matthew Estes
20 | Obtain users to test out the game | 2024-12-15 | 2025-01-26 | Matthew Estes
Milestone Number | Milestones | Start Date | End Date
0 | Concept Art | 2024-10-06 | 2024-11-24
1 | Main Menu | 2024-10-06 | 2024-10-27
2 | Basic Game Manager | 2024-10-27 | 2024-11-10
3 | Test Level w/ Player Character | 2024-11-10 | 2024-11-17
4 | Player Movement | 2024-11-10 | 2024-11-17
5 | Player Abilities | 2024-11-17 | 2024-12-15
6 | Test Enemy | 2024-11-17 | 2024-12-15
7 | Test Items 1 & 2 | 2024-12-15 | 2024-12-22
8 | Test Items 3 & 4 | 2024-12-22 | 2024-12-29
9 | Test Item Interactions | 2024-12-15 | 2024-12-29
10 | Enemy Movement | 2024-11-17 | 2024-12-22
11 | Enemy Attacks | 2024-12-15 | 2025-01-12
12 | Player Animations | 2024-12-15 | 2025-01-12
13 | Enemy Animations | 2024-12-22 | 2025-01-19
14 | Level Designs | 2024-10-13 | 2025-02-23
15 | Test Boss | 2024-12-22 | 2025-01-12
16 | Full Boss | 2025-01-12 | 2025-02-23
17 | Art Assets | 2024-10-27 | 2025-02-16
18 | More Enemies | 2025-02-16 | 2025-03-09
19 | More Items | 2025-01-05 | 2025-03-02
20 | More Bosses | 2025-01-12 | 2025-03-23
21 | Music | 2024-11-03 | 2025-03-30
22 | Save/Continue Game in Progress | 2025-03-02 | 2025-03-16

## Effort Matrix
Tasks | Lead Person | Matthew Estes Effort | Hari Koirala Effort | Vitta Silberberg Effort | Bailin Zhen Effort
Design and impelment the ability set of one unique character | Everyone | 25% | 25% | 25% | 25%
Design a respawn area for players to re-enter the game after dying | Hari Koirala | 15% | 50% | 15% | 20%
Implement composition for projectiles to enhance modularity and facilitate future expansions | Hari Koirala | 10% | 70% | 10% | 10%
Develop projectile functionality to ensure they behave as intended within the game | Hari Koirala | 20% | 50% | 15% | 15%
Research methods for creating a responsive player UI that adapts to different screen sizes and resolutions | Hari Koirala | 15% | 65% | 15% | 15%
Create a system for playing and managing character animations to enhance visual feedback during gameplay | Hari Koirala | 5% | 80% | 5% | 10%
Create a global signal system to handle events like onhit, ondamaged, enemydeath, for statistic tracking and passive activations | Bailin Zhen | 15% | 15% | 15% | 55%
Implement a sfx system into base character and base enemy scenes | Bailin Zhen | 10% | 10% | 10% | 70%
Design a standard way to hook up sounds to the sfx system in child character and enemy scenes | Bailin Zhen | 10% | 5% | 5% | 80%
Find, Purchase, or somehow Acquire all sounds and music needed for the game in the form of .wav files | Bailin Zhen | 20% | 10% | 20% | 50%
Develop a modular control scheme to be later modifiable by the UI Settings sytem | Bailin Zhen | 5% | 10% | 10% | 75%
Develop music and sound effects for levels, game events, or player actions | Vitta Silberberg | 0% | 0% | 100% | 0%
Design sprite sheets, art, and textures for game visuals and levels | Vitta Silberberg | 10% | 10% | 70% | 10%
Research level design for creating levels that feel fun to play through and explore | Vitta Silberberg | 10% | 5% | 80% | 5%
Design and implement player movement abilities and upgrades | Vitta Silberberg | 11% | 11% | 66% | 12%
Design unique discoverable items and discoverable upgrades | Vitta Silberberg | 20% | 20% | 40% | 20%
Design customizations for charater design | Matthew Estes | 55% | 10% | 25% | 10%
Develop detection and jump ability | Matthew Estes | 40% | 20% | 20% | 20%
Research optimization for projectile movement | Matthew Estes | 70% | 30% | 0% | 0%
Document the progress as the project moves along | Matthew Estes | 70% | 10% | 10% | 10%
Obtain users to test out the game | Matthew Estes | 55% | 15% | 15% | 15%
Concept Art | Vitta Silberberg | 0% | 0% | 100% | 0%
Main Menu | Hari Koirala | 20% | 50% | 15% | 15%
Basic Game Manager | Bailin Zhen | 10% | 10% | 10% | 70%
Test Level w/ Player Character | Matthew Estes | 50% | 15% | 15% | 20%
Player Movement | Matthew Estes | 70% | 10% | 10% | 10%
Player Abilities | Vitta Silberberg | 15% | 10% | 60% | 15%
Test Enemy | Hari Koirala | 15% | 75% | 10% | 10%
Test Items 1 & 2 | Bailin Zhen | 20% | 20% | 20% | 40%
Test Items 3 & 4 | Bailin Zhen | 10% | 15% | 10% | 65%
Test Item Interactions | Matthew Estes | 60% | 20% | 10% | 10%
Enemy Movement | Matthew Estes | 65% | 10% | 10% | 15%
Enemy Attacks | Hari Koirala | 15% | 60% | 15% | 10%
Player Animations | Vitta Silberberg | 10% | 10% | 70% | 10%
Enemy Animations | Vitta Silberberg | 10% | 10% | 70% | 10%
Level Designs | Vitta Silberberg | 10% | 10% | 70% | 10%
Test Boss | Hari Koirala | 15% | 55% | 15% | 15%
Full Boss | Bailin Zhen | 25% | 25% | 25% | 25%
Art Assets | Vitta Silberberg | 5% | 5% | 85% | 5%
More Enemies | Matthew Estes | 85% | 5% | 5% | 5%
More Items | Hari Koirala | 10% | 70% | 10% | 10%
More Bosses | Vitta Silberberg | 25% | 25% | 25% | 25%
Music | Vitta Silberberg | 5% | 5% | 85% | 5%
Save/Continue Game in Progress | Matthew Estes | 50% | 15% | 20% | 15%